## UTILITY IMPACT - GATES
GENERAL INFORMATION
| CONFLICT UTILITY ID LEGEND | UTILITY |  | DISPOSITION LEGEND:
| 1000 | CABLE AND TELECOMMUNICATION |  | RELOCATION, ADJUST, AND REMOVED
| 2000 | POWER (ELECTRICAL) |  | POTENTIAL RELOCATION
| 3000 | STORM DRAIN |  | PROTECT-IN-PLACE
| 4000 | WATER AND IRRIGATION
| 5000 | SEWER
| 6000 | GAS
ITEM NAME | INTERSECTION | PLAN SHEET NO. | SEGMENT NO. | UTILITY ID | UTILITY OWNER | CATEGORY/TYPE | SIZE/POTHOLE NO. | MATERIAL | PUNTO DE INSERCIÓN LEADER (DESCRIPCION) | PUNTO DE INSERCIÓN LEADER | DISPOSITION NOTES | ROW ACQUISITION | CITY/MTA ROW | DESIGNED BY | CONSTRUCTION BY | COLUMN 4 | PUNTOS QUE INTERVIENEN EN LA RED | TEXTO
RED1 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | WATER | 8" | UNKNOW | PA-1 | P32 | [6 empty] | P2-P7 | 8" DWPWS 9' N OF C/L
RED2 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | WATER | 12" | UNKNOW | PA-2 | P33 | [6 empty] | P9-P11 | 12" DWPWS 18' N OF C/L
RED2 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | WATER | - | UNKNOW | PA-6 | P37 | [6 empty] | P8 Y P11 | 12" DWPWS 23' W OF C/L
RED3 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | WATER | 12" | UNKNOW | PA-5 | P36 | [6 empty] | P12-P17 | POR DEFINIR
BLUE1 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | Reclaimed Water | 8" | Ductile Iron Pipe | PA-3 | P34 | [6 empty] | P18-P22 | INSTALL 8" RW D.I. PIPE
BLUE1 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | Reclaimed Water | 6" | Ductile Iron Pipe | PA-4 | P35 | [6 empty] | P22-P23 | INSTALL 6" RW D.I. PIPE
RED4 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | WATER | 4" | UNKNOW | PA-7 | P38 | [6 empty] | P24 Y P28 | 4" SCG 22' E OF C/L(ABAND)
RED4 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | WATER | 4" | UNKNOW | PA-8 | P39 | [6 empty] | P29-P31 | 4" SCG 34' E OF C/L
RED4 | CHANDLER BLVD | COLFAX AVE. |  |  | LADWPWS | WATER | - | UNKNOW | PA-9 | P40 | [6 empty] | P25-P27 | POR DEFINIR

## Hoja1
TEXTO
SCG 3" // 12'E C/L
PTέT ICa // 7' W C/L
PTέT ICa 6-69 ABAND // B2-09-88835 23'N C/L
PTT 1-4" DU // 27' N C/L B2-00-1148R
DWPPS 2-4" P 2-84 // 119' E C/L AJ-19155
DWPWS 6" // 21' S.N.
LAW D 6" // 12' W C/L (ABANDONED)
PTέT -2D 6' S.N. // 111' E. C/L
PTέT 2DU // 8' Nέ 7'E C/L
DWPWS 6" 12' S C/L
SCG 2" ABAND 2-73 // BWD 40333-002 8' N C/L
SCG 2" 2-73 14'N C/L // BWD 40333-002
DWPPS // 170' N. C/L SJ-69054
Prop. Sewer - GID 5
LAWD 6" // 12' W C/L
76'N C/L
45'N C/L
41'E C/L
69'E C/L
274'E C/L
PTέT 2D // 6' S.N. 111'E
PTT 1-2" DU 7-81 // 26.5'N C/L // B2-09-7177T
PTT B.C. // 24'N C/L
PTT VAR. DU 7-78 // 25'N C/L B2-09-1035R
DWPPS 2-4"P 12-80 // 27'N C/L-10632
DWPWS 3-72 // 75'W.E FLR 90829